## JCI
Project Name | QUANTA
Adress | 100 WEST BIG BEAVER SUITE 520
Contractor | Integrated Acoustical
Contractor Address | P.O Box 1544, Troy
Start Date | 2023-04-01
Completion Date | 2023-06-01
Project | START DATE | DURATION (days)
Demolition | 2023-04-01 | 10
Rough Framing | 2023-04-07 | 7
Rough Electrical | 2023-04-17 | 10
Drywall work | 2023-04-24 | 10
Fire Suppression | 2023-04-25 | 5
HVAC work | 2023-04-25 | 5
Fire Alarm Work | 2023-04-26 | 2
Finish Drywall | 2023-05-01 | 3
Paint Work Drywall | 2023-05-08 | 10
Install Doors | 2023-05-11 | 2
IT work | 2023-05-11 | 10
Final Electrical | 2023-05-15 | 2
Install Ceiling Tile | 2023-05-15 | 2
Final HVAC | 2023-05-15 | 2
Millwork install | 2023-05-15 | 1
Plumbing install | 2023-05-16 | 1
Flooring Install | 2023-05-18 | 2
furniture Move in | 2023-05-24 | 4
Wire up furniture | 2023-05-29 | 1
cleanup and punchlist | 2023-05-30 | 2
Tenant occupancy | 2023-06-01 | 1